## Login Test Cases
Test Scenario ID | TS_002
Test Scenario Name | Validate Login Functionality
Project | DemoBlaze Product Store
Module | User Authentication - Login
Created By | MH Lohith
Creation Date | 08-03-2026
Priority | P0 - Critical
Test Case ID | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC_LI_001 | Verify login with valid registered username and password | 1. Click on 'Log in' link 2. Enter valid registered username 3. Enter correct password 4. Click 'Log in' button | Username: validuser123 Password: Valid@123 | 1. User logged in successfully 2. Username displayed in navbar 3. Modal closes 4. Redirected to home page 5. 'Log in' changes to 'Log out' | 1. User logged in successfully 2. Username displayed in navbar 3. Modal closes 4. Redirected to home page 5. 'Log in' changes to 'Log out' | Pass | P0 | Happy path - valid credentials
TC_LI_002 | Verify login persistence across page navigation | 1. Login with valid credentials 2. Navigate to different pages 3. Verify login status 4. Refresh page | Username: validuser123 Password: Valid@123 | 1. User remains logged in across pages 2. Session persists after refresh 3. Username visible on all pages | 1. User remains logged in across pages 2. Session persists after refresh 3. Username visible on all pages | Pass | P0 | Session management validation
TC_LI_003 | Verify login with alphanumeric username | 1. Click 'Log in' 2. Enter alphanumeric username 3. Enter correct password 4. Click 'Log in' button | Username: User123Test Password: Pass@123 | User logged in successfully | User logged in successfully | Pass | P0 | Valid format - alphanumeric
TC_LI_004 | Verify login remembers last successful username (if feature exists) | 1. Login successfully 2. Logout 3. Click 'Log in' again 4. Check username field | Username: validuser123 Password: Valid@123 | empty based on design | empty based on design | Pass | P2 | User convenience feature
TC_LI_005 | Verify login with unregistered username | 1. Click 'Log in' 2. Enter username that doesn't exist 3. Enter any password 4. Click 'Log in' button | Username: nonexistentuser Password: Any@123 | 1. Error message: 'User does not exist' 2. User not logged in 3. Modal remains open | 1. Error message: 'User does not exist' 2. User not logged in 3. Modal remains open | Pass | P0 | Invalid username validation
TC_LI_006 | Verify login with valid username but wrong password | 1. Click 'Log in' 2. Enter valid registered username 3. Enter incorrect password 4. Click 'Log in' button | Username: validuser123 Password: WrongPass@123 | 1. Error message: 'Wrong password' 2. User not logged in 3. Modal remains open | 1. Error message: 'Wrong password' 2. User not logged in 3. Modal remains open | Pass | P0 | Password validation
TC_LI_007 | Verify login with empty username | 1. Click 'Log in' 2. Leave username field blank 3. Enter password 4. Click 'Log in' button | Username: [Empty] Password: Valid@123 | 1. Error message: 'Please fill out Username and Password' 2. User not logged in | 1. Error message: 'Please fill out Username and Password' 2. User not logged in | Pass | P0 | Mandatory field validation
TC_LI_008 | Verify login with empty password | 1. Click 'Log in' 2. Enter valid username 3. Leave password field blank 4. Click 'Log in' button | Username: validuser123 Password: [Empty] | 1. Error message: 'Please fill out Username and Password' 2. User not logged in | 1. Error message: 'Please fill out Username and Password' 2. User not logged in | Pass | P0 | Mandatory field validation
TC_LI_009 | Verify login with both fields empty | 1. Click 'Log in' 2. Leave both fields blank 3. Click 'Log in' button | Username: [Empty] Password: [Empty] | 1. Error message: 'Please fill out Username and Password' 2. User not logged in | 1. Error message: 'Please fill out Username and Password' 2. User not logged in | Pass | P0 | Mandatory fields validation
TC_LI_010 | Verify login with username containing spaces only | 1. Click 'Log in' 2. Enter only spaces in username 3. Enter valid password 4. Click 'Log in' button | Username: ' ' Password: Valid@123 | Error message displayed, user not logged in | Popup displays wrong password | Fail | P1 | Invalid input validation
TC_LI_011 | Verify login with password containing spaces only | 1. Click 'Log in' 2. Enter valid username 3. Enter only spaces in password 4. Click 'Log in' button | Username: validuser123 Password: ' ' | Error message displayed, user not logged in | Error message displayed, user not logged in | Pass | P1 | Invalid password validation
TC_LI_012 | Verify login with incorrect case in username | 1. Click 'Log in' 2. Enter username with wrong case 3. Enter correct password 4. Click 'Log in' button | Username: VALIDUSER123 (if stored as validuser123) Password: Valid@123 | failure based on case sensitivity rules | failure based on case sensitivity rules | Pass | P1 | Case sensitivity validation
TC_LI_013 | Verify password field masking | 1. Click 'Log in' 2. Enter username 3. Type password 4. Verify characters are masked | Username: validuser123 Password: Valid@123 | Password characters displayed as dots/asterisks | Password characters displayed as dots | Pass | P0 | Security - password masking
TC_LI_014 | Verify login after multiple failed attempts | 1. Try to login with wrong password 5 times 2. Then try with correct password | Username: validuser123 Password: Wrong@123 (5 times), then Valid@123 | Account locked | Account locked | Pass | P0 | Brute force protection
TC_LI_017 | Verify password is not visible in page source | 1. Click 'Log in' 2. Enter credentials 3. View page source (Ctrl+U) 4. Check if password visible | Username: validuser123 Password: Valid@123 | Password not visible in plain text in source | Password not visible in plain text in source | Pass | P0 | Security - password exposure
TC_LI_018 | Verify password is encrypted during transmission | 1. Open browser dev tools (Network tab) 2. Click 'Log in' 3. Enter credentials 4. Submit 5. Check network request | Username: validuser123 Password: Valid@123 | 1. Request sent via HTTPS 2. Password encrypted/hashed in payload | 1. Request sent via HTTPS 2. Password encrypted/hashed in payload 3.To be discussed with non-functional team | Pass | P0 | Security - password transmission
TC_LI_019 | Verify session token security | 1. Login successfully 2. Check cookies/session storage 3. Verify token properties | Username: validuser123 Password: Valid@123 | 1. Session token is secure 2. HttpOnly flag set 3. Secure flag set for HTTPS | To be discussed with non-functional team | N/A | P0 | Security - session management
TC_LI_020 | Verify 'Close' button functionality | 1. Click 'Log in' to open modal 2. Enter some data 3. Click 'Close' button | N/A | 1. Modal closes 2. Data not saved 3. User returns to home page 4. Not logged in | 1. Modal closes 2. Data not saved 3. User returns to home page 4. Not logged in | Pass | P0 | Cancel operation validation
TC_LI_021 | Verify 'X' (close icon) functionality | 1. Click 'Log in' to open modal 2. Enter some data 3. Click 'X' icon | N/A | 1. Modal closes 2. Data not saved 3. User not logged in | 1. Modal closes 2. Data not saved 3. User not logged in | Pass | P0 | Alternative close method
TC_LI_022 | Verify clicking outside modal behavior | 1. Click 'Log in' to open modal 2. Click outside the modal area | N/A | Modal closes | Modal closes | Pass | P1 | Modal behavior validation
TC_LI_023 | Verify tab navigation in login form | 1. Click 'Log in' 2. Press Tab key from username field 3. Verify cursor moves to password 4. Tab again to Log in button | N/A | Tab navigation works correctly in sequence | Tab navigation works correctly in sequence | Pass | P1 | Keyboard accessibility
TC_LI_024 | Verify Enter key submits the form | 1. Click 'Log in' 2. Enter valid credentials 3. Press Enter key | Username: validuser123 Password: Valid@123 | Form submitted, user logged in successfully | Enter key responds | Pass | P1 | Keyboard shortcut functionality
TC_LI_025 | Verify form labels are properly displayed | 1. Click 'Log in' 2. Verify 'Username:' label 3. Verify 'Password:' label | N/A | 1. All labels visible and aligned 2. Labels are readable | no inputs has labels | Fail | P2 | UI/UX validation
TC_LI_026 | Verify modal title displays correctly | 1. Click 'Log in' 2. Check modal header | N/A | 'Log in' title displayed prominently at top | 'Log in' title displayed prominently at top | Pass | P2 | UI validation
TC_LI_027 | Verify login button state | 1. Open login modal 2. Verify button appearance 3. Check if clickable | N/A | Button is enabled and clickable | Button is enabled and clickable | Pass | P1 | Button functionality
TC_LI_028 | Verify input field focus states | 1. Click 'Log in' 2. Click on username field 3. Click on password field 4. Check visual feedback | N/A | Fields show focus indicator (border/highlight) | Fields show focus indicator (border/highlight) | Pass | P2 | UI/UX - focus states
TC_LI_029 | Verify logout functionality | 1. Login successfully 2. Click 'Log out' link 3. Verify logout | Username: validuser123 Password: Valid@123 | 1. User logged out 2. Session cleared 3. 'Log out' changes to 'Log in' 4. Username removed from navbar | 1. User logged out 2. Session cleared 3. 'Log out' changes to 'Log in' 4. Username removed from navbar | Pass | P0 | Logout functionality
TC_LI_030 | Verify session timeout handling | 1. Login successfully 2. Leave idle for extended time 3. Try to perform action | Username: validuser123 Password: Valid@123 | 1. Session expires after timeout 2. User prompted to login again 3. Appropriate message shown | To be discussed with non-functional team | N/A | P1 | Session timeout validation
TC_LI_031 | Verify user cannot login twice simultaneously | 1. Login in browser 1 2. Try to login same user in browser 2 3. Check behavior | Username: validuser123 Password: Valid@123 | Second login succeeds | Second login succeeds | Pass | P1 | Concurrent session handling
TC_LI_033 | Verify login functionality on Chrome browser | 1. Open Chrome browser 2. Navigate to application 3. Test login | Username: chromeuser Password: Valid@123 | Login works correctly on Chrome | Login works correctly on Chrome | Pass | P0 | Cross-browser - Chrome
TC_LI_034 | Verify login functionality on Firefox browser | 1. Open Firefox browser 2. Navigate to application 3. Test login | Username: firefoxuser Password: Valid@123 | Login works correctly on Firefox | Login works correctly on Firefox | Pass | P0 | Cross-browser - Firefox
TC_LI_035 | Verify login functionality on Safari browser | 1. Open Safari browser 2. Navigate to application 3. Test login | Username: safariuser Password: Valid@123 | Login works correctly on Safari | Login works correctly on Safari | Pass | P1 | Cross-browser - Safari
TC_LI_036 | Verify login functionality on Edge browser | 1. Open Edge browser 2. Navigate to application 3. Test login | Username: edgeuser Password: Valid@123 | Login works correctly on Edge | Login works correctly on Edge | Pass | P1 | Cross-browser - Edge
TC_LI_037 | Verify login modal on mobile devices | 1. Open app on mobile device 2. Click 'Log in' 3. Verify modal responsiveness 4. Test login | Username: mobileuser Password: Valid@123 | 1. Modal fits screen properly 2. All elements accessible 3. Login successful | 1. Modal fits screen properly 2. All elements accessible 3. Login successful | Pass | P0 | Mobile responsiveness
TC_LI_038 | Verify login modal on tablet devices | 1. Open app on tablet 2. Click 'Log in' 3. Verify modal display 4. Test login | Username: tabletuser Password: Valid@123 | Modal displays correctly, login works | Modal displays correctly, login works | Pass | P1 | Tablet responsiveness
TC_LI_039 | Verify touch interactions on mobile | 1. Open on mobile device 2. Click 'Log in' 3. Tap fields and buttons 4. Complete login | Username: touchuser Password: Valid@123 | All touch interactions work smoothly | All touch interactions work smoothly | Pass | P0 | Mobile touch functionality
TC_LI_040 | Verify login response time | 1. Click 'Log in' 2. Enter valid credentials 3. Click 'Log in' button 4. Measure response time | Username: perfuser Password: Valid@123 | 1. Response time < 2 seconds 2. Immediate feedback provided | 1. Response time < 2 seconds 2. Immediate feedback provided | Pass | P1 | Performance validation
TC_LI_041 | Verify multiple rapid login attempts | 1. Open login modal 2. Submit form rapidly 10 times 3. Check system response | Username: validuser123 Password: Valid@123 | System handles rapid requests gracefully | System handles rapid requests gracefully | Pass | P1 | System stability
TC_LI_042 | Verify login under slow network conditions | 1. Simulate slow 3G network 2. Attempt to login 3. Check user experience | Username: validuser123 Password: Valid@123 | 1. Loading indicator shown 2. Login completes or timeout with message | To be discussed with non-functional team | N/A | P1 | Network resilience
TC_LI_043 | Verify login with copy-pasted credentials | 1. Copy username from external source 2. Click 'Log in' 3. Paste username and password 4. Submit | Username: copieduser Password: Copied@123 | Login works with copy-pasted data | Login works with copy-pasted data | Pass | P1 | Copy-paste functionality
TC_LI_044 | Verify login with leading/trailing spaces | 1. Click 'Log in' 2. Enter ' username ' with spaces 3. Enter ' password ' with spaces 4. Submit | Username: ' validuser123 ' Password: ' Valid@123 ' | error shown | it reads the spaces as well | Fail | P1 | Input sanitization
TC_LI_045 | Verify login after page refresh | 1. Click 'Log in' 2. Enter credentials 3. Refresh page 4. Click 'Log in' again 5. Submit | Username: refreshuser Password: Valid@123 | Login works correctly after refresh | What ever the user has typed it has been deleted after the refresh | Fail | P2 | Page refresh handling
TC_LI_046 | Verify login with special characters in password | 1. Click 'Log in' 2. Enter username 3. Enter password with special chars 4. Submit | Username: validuser Password: P@ss#w0rd! | Login successful with special characters | Login successful with special characters | Pass | P1 | Special character support
TC_LI_047 | Verify login redirect to previous page | 1. Browse to a product page 2. Click 'Log in' 3. Complete login 4. Check redirect | Username: validuser123 Password: Valid@123 | User redirected back to home page | User redirected back to home page | Pass | P2 | Redirect behavior
TC_LI_048 | Verify error message persistence | 1. Login with wrong credentials 2. See error message 3. Correct credentials and login | Username: validuser123 Password: Wrong@123, then Valid@123 | 1. Error shown for wrong credentials 2. Error cleared after successful login | 1. Error shown for wrong credentials 2. Error cleared after successful login | Pass | P1 | Error handling
TC_LI_049 | Verify browser autofill compatibility | 1. Enable browser password manager 2. Login and save credentials 3. Logout 4. Click 'Log in' 5. Check autofill | Username: validuser123 Password: Valid@123 | Browser autofill works correctly | Browser has no autofill option right now | Fail | P2 | Browser integration
TC_LI_050 | Verify Caps Lock warning (if exists) | 1. Click 'Log in' 2. Enable Caps Lock 3. Type in password field | N/A | Warning shown that Caps Lock is on | No warning is shown | Fail | P2 | User assistance feature
TEST SUMMARY
Total Test Cases: | 47
P0 Test Cases: | 20
P1 Test Cases: | 19
P2 Test Cases: | 8
Not Executed: | 0